## Sheet3
Row Labels | Count of Automation Name
Abhishek H | 3
(blank) | 3
On Hold | 1
(blank) | 2
Ashish | 10
(blank) | 10
Completed | 5
In progress | 1
Issue | 1
Issue | 1
Waiting for test data | 1
(blank) | 1
Ayush | 3
(blank) | 3
Completed | 1
(blank) | 2
Bharath | 4
(blank) | 4
Completed | 1
Completed | 2
(blank) | 1
Haribabu | 1
(blank) | 1
On Hold | 1
Harsha | 3
6th Jan - 17th Jan | 1
(blank) | 2
(blank) | 2
Himabindu | 4
(blank) | 4
Completed | 1
(blank) | 3
Piyush | 3
(blank) | 3
Completed | 2
Issue | 1
Praveen | 1
(blank) | 1
Completed | 1
Pravin | 2
(blank) | 2
Completed | 1
Waiting for test data | 1
Ramesh | 19
6th Jan - 17th Jan | 1
6th Jan - 17th Jan | 1
Completed | 1
(blank) | 17
Completed | 8
In progress | 1
Issue | 1
On Hold | 3
Waiting for test data | 1
(blank) | 3
Rekha | 2
(blank) | 2
Completed | 1
(blank) | 1
Sameera | 7
6th Jan - 17th Jan | 2
(blank) | 5
Completed | 2
Waiting for test data | 1
(blank) | 2
Sandip | 3
(blank) | 3
Completed | 2
(blank) | 1
Scott | 1
(blank) | 1
Completed | 1
Seerisha | 1
(blank) | 1
(blank) | 1
Shreyank | 1
(blank) | 1
(blank) | 1
Yaswanth | 9
(blank) | 9
Completed | 4
Issue | 1
On Hold | 1
Waiting for test data | 1
(blank) | 2
Yaswanth/Piyush | 1
(blank) | 1
Waiting for test data | 1
(blank) | 48
6th Jan - 17th Jan | 2
(blank) | 46
Completed | 5
(blank) | 41
Grand Total | 126

## Sheet1
Automation Name | Developer |  | Cloud PC Tested | Code Change (D Drive) | Batch | Code Changes (SAP 770) | Target Date | Unattended | Configuration | Development Status | Dev Testing Status | Challenges faced during testing with Date | Comments/Feedback
US Demand Split and Allocation | Bharath |  | Y | Y | 1 | Not required |  | Completed | Completed | Completed | Completed
DMR Automation |  |  | Y | Y | 1 | Required |  | Completed | Completed | Completed | Completed
CSM Medicaid CLD | Ashish |  |  | Y | 1 |  | 2025-03-01 | Completed | Completed | Completed | Issue | System exception came
Master File & Open Items | Rishi |  | Y | Y | 2 | Required |  | Completed | Completed | Re-work | Enhancement | Production issue
Summit - User Training Management | Bharath |  | Y | Y | 2 | Not required |  | Completed | Completed | Completed | In progress
Case Narrative | Sandip |  | Y | Y | 2 | Not required | 30/1/2025 | Completed | Completed | Completed | Completed
MSR Reports |  |  | Y | Y | 1 | Not required |  | Completed | Completed | Completed | Completed |  | Decommissioned
MASR EMEA | Harsha |  | Y | Y | 1 | Not Required | 2024-04-12 | Completed | Completed | Completed | Completed
ClinMVReport | Sameera |  | Y | Y | 1 | Not Required | 2024-04-12 | Completed | Completed | Completed | Completed
Custom RAVE Reports | Sameera |  | Y | Y | 1 | Not Required | 2024-04-12 | Completed | Completed | Completed | Completed
RAP Safety | Pravin |  | Y | Y | 1 | Not required | 2024-11-12 | Completed | Completed | Completed | Completed
Analysis Output Consistency Check | Sameera |  |  | Y | 1 | Completed | 2025-03-01 | Completed | Completed | Completed | Completed
Dispute Resolution P1 P2 | Ashish |  | Y | Y | 2 | Required | 2025-07-01 | Completed | Completed | Completed | Completed
IP DOCKETING | Ramesh |  |  |  | 2 |  | 23/12/2024 | Completed | Completed | Completed | Completed
SCG eLOC Automation - Vizient | Piyush |  | Y | Y | 2 | Not required |  | Completed | Completed | Completed | Issue | 2/14/2025: throwing Systen Exception- File Not Found
DEPUY - CoA & CoS Certificates Automation | Yaswanth |  | Y | Y | 1 | Not required | 17/12/2024 | Completed | Completed | Completed | Completed
IPIM MAILBOX RECONCILIATION_MainProcess | Yaswanth |  | Y | Y | 1 | Not required | 17/12/2024 | Completed | Completed | Completed | Completed
JJRC Audit Automation | Yaswanth |  | Y | Y | 1 | Not required | 18/12/2024 | Completed | Completed | Completed | Completed
SA Quotation PhaseII | Bharath |  | Y | Y | 1 | Required | 30/12/2024 | Completed | Completed | Completed | Completed
RAVE Refresh Views | Sameera |  | Y | Y | 1 | Completed | 31/12/2024 | Completed | Completed | Completed | Completed
JJV Agile & Qumas Export Print | Ramesh |  |  |  | 1 |  | 2025-06-01 | Completed | Completed | Completed | Completed
RSC Flag Automation | Ayush |  |  | Y | 1 | Required | 20/1/2024 |  | Completed | Completed | Completed
RSC - PARM Data Migration | Piyush |  | Y | Y | 1 | Not required | 27/12/2024 | Completed | Completed | Completed | Completed
Ethicon CO Reminders | Ramesh |  | Y | Y | 1 | Not required | 2024-09-12 | Completed | Completed | Completed | Completed
VTMF Document Upload | Ramesh |  | Y | Y | 1 | Not Required | 2024-05-12 | Completed | Completed | Completed | Completed
BRQC CARE(Contracted Automated Review Examiner) | Ashish |  | Y | Y | 1 | Not required | 2025-09-01 | Completed | Completed | Completed | Completed
BWI AP Process Automation | Ramesh |  | Y | Y | 1 | Not Required | 2024-04-12 | Completed | Completed | Completed | Completed
Flex QOP | Ramesh |  | Y | Y | 1 | Not required | 2024-11-12 | Completed | Completed | Completed | Completed
SCG Contracting Management – eLOC HPG | Ramesh |  | Y | Y | 2 | Not required | 29/12/2024 | Completed | Completed | Completed | Completed
Controlled Substance Data Collection | Priya |  |  | Y | 2 |  | 29/12/2024 | Completed | Completed | Completed | Completed
ETS PQMS Complaints Management | Ramesh |  | Y | Y | 1 | Required | 13/1/2025 | Completed | Completed | Completed | Completed
LATAM Invoice Rejection | Ramesh |  | Y | Y |  | Not required | 2025-08-01 | Completed | Completed | Completed | Completed
Acuvue Ability | Bharath |  | Y | Y | 1 | Not required | 16/1/2024 | Completed | Completed | Completed | Completed
eLIMS User Access Review Automation | Ramesh |  | Y | Y | 1 | Required | 15/1/2025 | Completed | Completed | Completed | Completed
OTIF FIFO | Ramesh |  |  | Y | 1 |  | 2025-01-17 | Completed | Completed | Completed | Completed
Product Load into MDRIM | Ramesh |  |  |  | 2 |  | 26/12/2024 | Completed | Completed | Completed | Completed
Brazil Warehouse | Rishi |  |  | Y | 2 | Inprogress | 2025-04-01 | Completed | Completed | In Progress | Waiting for test data
SDIA / Trails 2 You | Harsha |  |  |  | 2 | Required | 16/12/2024 | Completed | Completed | Completed | Completed
RND ESDCAQ | Pravin |  |  | Y | 2 |  | 2024-12-12 |  | Completed | Enhancement | Enhancement |  | Enhancement in progress
CADTH web scraping | Ramesh |  | Y | Y | 2 | Not Required | 2024-05-12 | Completed | Completed | Completed | Completed
Rebate Payments Phase 2 | Pravin |  |  | Y | 1 | Not required | 2025-10-01 | Completed | Completed | Completed | Completed
DCS Product Conversion | Rekha |  |  | Y | 1 |  | 14/1/2025 | Completed | Completed | Completed | Completed
ETH Manual Order Allocation | Yaswanth |  |  | Y | 2 | Required | 2024-06-12 |  | Completed | In Progress | Waiting for test data |  | out of 3 sub processes, one process has be completed end to end. Waiting for test data and SAP T-Code access for remaining 2 sub processes
CS Clinical Distribution | Ashish |  |  | Y | 1 | Required | 21/1/2025 |  | Completed | Completed | Completed
R&D JEISR | Yaswanth |  |  | Y | 2 |  | 24/01/2025 | Completed | Completed | Completed | Completed
Missed Shipment Communication | Ashish |  | Y | Y | 1 | Required | 2025-07-01 | Completed | Completed | Completed | Completed
w3 | Balaji |  |  | Y |  |  | 20/12/2024 |  |  | YTS |  |  | Currently this process is in hypercare and developers are still working on some issues for it.
Sales Order Creation | Ashish |  | Y | Y | 1 | Required | 2025-08-01 | Completed | Completed | Completed | Completed
USROTC RAD Supply Preference | Piyush |  |  | Y | 1 | Required | 15/1/2025 | Completed | Completed | Completed | Completed
CAR-T | Yaswanth |  |  | Y | 2 | Not required |  |  | Completed | Completed | Completed |  | Bot completed Items for Phase 1
CAR-T MVP 2 | Yaswanth |  |  | Y | 2 | Required |  |  | Completed | Completed | Waiting for test data
EMEA Invoice Extract&Deliver | Ramesh |  |  | Y | 2 | Required | 2025-07-01 |  | Completed | Completed | Waiting for test data |  | 6/02/2025-Requested test data to business
Order Entry Automation – Fusion | Ramesh |  |  | Y | 2 | Required |  |  | Completed | Completed | Completed |  | 6/02/2025- Requested test data
SPACE User Access | Haribabu | Akshay |  |  | 3 |  |  |  |  | Enhancement | Enhancement |  | Enhancemennt is in progress
ZOE R3-Abiliti Overnight | Bharath |  |  | Y | 1 | Required | 2025-01-10 | Completed | Completed | Completed | Completed
Tax - Indiebot | Ramesh |  |  | Y | 2 | Required | 23/12/2024 | Completed | Completed | Completed | Completed |  | 4/2/2025-Unable to Download invoice in SAP even manually; Checking with SE
Tender Header Analysis-Detection |  |  |  |  | 3 | [7 empty] | Abbyy Process
Small Molecule Digital Release | Ramesh |  |  | Y | 2 | Required |  |  | Completed | In progress | YTS
Raw Material Release | [6 empty] | 19/12/2024 | [5 empty] | About to decomission
ASPAC Vision I2C |  |  |  |  | 3 | [7 empty] | Abbyy Process
CMO Onboarding | Ashish |  | Y | Y |  | Required | 2024-10-01 | Completed | Completed | Completed | Completed
SC Plan PO Management EMEA | Rekha | Rajani |  | Y | 3 | Required |  |  |  | Completed |  |  | 14/02/2025: 1.Latest code is updated in the BP upgraded Verion ,SE need to check with Badri 2.SAP Connection configuration is failing SE provided SAP team contact details ,dropeed mail to SAP team 3.Credentials which are used in the code unable to find out in BP 7.0
G3O Invoicing | Ashish |  |  | Y | 1 |  | 23/12/2024 |  | Completed | Completed | Completed
HR TA - ORW Offer Generation | [12 empty] | Decomissioned
eCRF&aECG | Ashish |  | Y | Y | 2 | Not required |  | Completed | Completed | Enhancement | Enhancement
Printing of Finished Good Labels from PRISYM 360 | Abhishek H |  |  | Y | 2 |  | 18/12/2024 |  | Completed | Completed | Hold |  | 1/29/2025: Application got installed, waiting for few of the field's access. Reach out Manish Garg for help.
R&D EISFAF | Ramesh |  |  | Y | 2 | Not required | 20/12/2024 |  | Completed | Enhancement | Enhancement |  | 31/01/2025 - SE mentioned it will take around a week for enahncement
LA_SCM_MT-SAP-CONTRACTCREATION | Ashish |  |  |  | 2 |  |  |  | Completed | Completed | Completed
OMP Omega | Abhishek Kumar |  |  |  | 3
Change Admin (CA) Check II | Ashish |  |  |  | 3 | [7 empty] | Decommissioned
LATAM Customer Order Intake | Yaswanth/Piyush |  |  | Y | 2 | Required | 2024-05-12 |  | Completed | Enhancement | Enhancement |  | 31/01/2025-SAP version change is happening in 7.0 so out on hold
Inventory Reconciliation GMED | Ashish |  |  |  | 2 |  | 26/12/2024 |  | Completed | Completed | Hold | Machine do not have access to Excel file
DPS SAFETY STOCK | Ashish |  |  |  | 3 | [5 empty] | Hold | On Hold due to code Enhancement
R&D Submission Checks | Ashish |  |  | Y | 2 |  |  |  | Completed | Completed | Issue | 2/14/2025: credtional issue
Backorder Allocation | Ramesh |  |  | Y | 2 |  | 2025-10-01 |  | Completed | Completed | Waiting for test data |  | If test data needs B002 plant - then business may not be able to help. Test data prep is a challenge. Need to discuss with Dylan.
ADAM Submission Check | Haribabu |  |  | Y | 2 | Required | 23/1/2025 | Completed | Completed | Completed | Completed
WorkOrder Due Date Automation | Ashish |  |  |  | 3 | [7 empty] | Decommissioned
Middle East K5 Creation | Yaswanth |  |  | Y | 2 |  | 30/12/2024 |  | Completed | Completed | In Progress | 2/13/2025 : Data is not getting loaded to Queue | Waiting for Test data from Sajith
Returns Management - RGA Sharing | Ashish | Akshay |  |  | 3 | Required |  |  |  | In Progress |  |  | Email for Test Data has been sent to business by SE
Participant & Site Journey Maps | Yaswanth |  |  | Y | 2 |  | 2024-02-01 | Completed | Completed | Completed | Completed
Order Monitoring Automation | Ashish | Rajani |  | Y | 3 |  |  |  |  | Completed |  |  | Power apps and Azure database access is pending ,informed SE
CSM Chargeback | Yaswanth | Akshay |  |  | 3 | Required |  |  |  | Completed | Waiting for test data |  | Test Data is not available as per SE Test Da for this process comes from Core Chargeback process
ME Order Automation | Ashish | Mayura |  | Y | 3 |  |  |  |  | Completed | In Progress
ICP-SAP BTB LATAM COMMERCIAL Yearend (H) | Ashish |  |  |  | 3 |  |  |  |  | Hold | Hold |  | This process runs yearly - No updates in this process since long
WebTos | Sandip |  | Y | Y |  | Not required | 16/1/2024 | Completed | Completed | Completed | Completed
CSM Pay Package | Yaswanth | Mayura | Y | Y | 3 |  |  |  |  | Completed | Hold |  | Vi mod access raised
GCC Reporting | Yaswanth
Document Reference Replacement | Yaswanth |  | Y | Y | 2 | Not required | 2025-07-01 | Completed | Completed | Completed | Completed
SCG eLOC Premier | Yaswanth
Task Reminders & Escalations | Yaswanth
Atlas Material Flag for deletion | Sameera |  |  | Y | 2 | Completed | 26/12/2024 | Completed | Completed | Completed | Completed
Croom PO Generation | Sameera |  |  | Y | 2 |  |  |  | Completed
Simple Submission Readiness Checks | Sandip |  | Y | Y |  | Not required | 2025-09-01 | Completed | Completed | Completed | Completed
RPA-GL-PHM-RND-CMS (NeuroScience) | Chandana |  |  |  | 2 |  |  |  | Completed | Enhancement | Enhancement
CSM Medicaid Invoice Phase-1 and 2 | Sireesha |  |  |  | 2 |  |  |  |  | Bug fixes | Bug fixes
Non GMED PO | Ankamma Rao |  |  |  | 2 | Required | 45870 |  | Completed | Completed | Completed
Archiving Auto Index | Ashish |  |  |  | 2 |  |  |  | Completed | Bug fixes | Bug fixes
CRO Site Payments v2 | Ramesh |  |  |  | 3
Turkey Order Automation | Ramesh | Mayura |  |  | 3 |  |  |  |  | Completed | Hold |  | Vi mod access raised
NA_RND_RAVE_UPDATE_USERACCESS | Ramesh |  |  |  | 3
CORE Chargebacks | Yaswanth | Akshay |  |  | 3 |  |  |  |  | Bug Fixes | Bug fixes |  | Bug fix for production isssue is in progress
QA Master Data | Lokesh |  |  |  | 2 |  | 24/12/2024 |  | Completed | Bug fixes | Bug fixes
RSC-RAD Restrictions | Ayush |  | Y | Y | 1 | Required | 13/1/2025 | Completed | Completed | Completed | Completed
BWI Manual Allocation | Yaswanth |  |  |  | 3 |  | 20/12/2024
RA-VARIATIONS-OUTCOMES_MainProcess | Rekha | [5 empty] | 23/12/2024 |  | On Hold | On Hold
GCO Site Manager Training - RED Chatbot | Ramesh | Rajani |  |  | 3 | [7 empty] | Decommissioned
RAD Supply Preference | Bharath |  |  |  | 2 | Required | 2025-02-06 |  | Completed | Completed | Completed
HCP Payments Germany | Ashish |  |  |  | 2 |  | 19/12/2024 |  | Completed | Completed | Completed
GR MATCH | Piyush |  |  | Y |  | Not required | 27/12/2024 |  | Completed | Completed | Issue | 1/22/2025- The field 'Customer PO' doesn't exist within this collection ( field missing in input sheet)
Joints & Mitek | Ashish |  |  | Y | 2 |  | 20/12/2024 |  | Completed | In Progress | waiting for test data | 2/11 - Valid Input data required for testing. Present data has one item and has Business exception
OPD TLF | Chandana
PIPE-Line Import | Himabindu
Master file open item phase 2 | Rishi
DPS Order Automation | Lokesh
SMOX Invoice Reconciliation Phase-2 | Ramesh |  |  |  | 2 |  |  |  | Completed | Completed | Enhancement
CVENTS Event Creation Automation | Yaswanth
CONTROLLEDSUBSTANCEINTERNETSEARCH
STO Flag Optimization | Ashish | [8 empty] | Hold | Hold |  | On Hold - Hypercare
WorkOrder Due Date Phase 2 | Chandana
Finish Goods Optimization | Yaswanth |  | Y | Y | 2 | Required | 2025-01-29 |  | Completed | On Hold | waiting for test data | 2/01/2025: Given test data is not resulting expected out come. SE is working with Business Team to get new test data
HCP Payment Austria | Ashish |  |  |  | 3 |  |  |  |  | In Progress

## Todays Status
Batch-1(Development)-38 |  |  |  | Batch-1(QA)-38
Status | Count | ETA | Remark | Status | Count | ETA | Remark
Testing In Progress | 0 |  | Team currently working on these process | Deployment completed | 37 Non-Gxp- 21 Gxp: 16
Issues | 0 |  | Dev changes, Bug fixes, Got feedback in Dev testing | QA Testing In Progress | 2
Hold | 0 |  | Enhancement, Pending with Application Team, Pending for application access | Issues | 9
Waiting for Test Data | 0 |  |  | Hold | 2 |  | Re-deployment
Total Completion count of Previous Day | 38 |  |  | Waiting for Credential/ env variable update | 1
|  |  |  | Sent for Review |  |  | Approvers needs to be mapped in Jira
Total Completion count of Today | 38 |  |  | Waiting for Test Data | 3
|  |  |  | Gxp Completion count | 5
|  |  |  | Non-Gxp Completion count | 15
|  |  |  | Total completion count of today | 1
|  |  |  | Total Completion count | 20
Batch-2(Development) - 44
Status | Count | ETA | Remark
Development Completed | 29
Development InProgress | 4
Testing in Progress | 2 |  | Team currently working on these process
Issues/Hold | 3 |  | Dev changes, Got feedback in Dev testing, Pending with Application Team, Pending for application access
Enhancement | 7
Bug Fixes | 3
Waiting for Test Data | 6
Total Completion count of Previous Day | 20
Total Completion count of Today | 20
Batch-3(Development) - 20
Status | Count | ETA | Remark
Development Completed
Development InProgress
Testing in Progress
Issues/Hold
Enhancement
Bug Fixes
Waiting for Test Data
Total Completion count of Previous Day
Total Completion count of Today
Note on B29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should this say "Batch 3?" Reply: Yes, It would be Batch 3, It was just in draft version, I changed it, Thanks!

## QA1_Status
Automation Name | GxP/Non-GxP | Developer | SE | Release Shared | Type | Release Name | Status | Comments | Jira Links
DEPUY - CoA & CoS Certificates Automation | Gxp | Yaswanth | Abhishek Kumar | Yes | Type 1 | GL_QNC_COACOSGENERATION_R1.17 | Hold - Redeployment | Enhancement in 7.0 | https://jira.jnj.com/browse/AEZX-1983
JJRC Audit Automation | Non-Gxp | Yaswanth | Abhishek Kumar | Yes | Type 1 | GL_SCM_JJRCAUDIT_R2.2_02122025 | Completed | 2/14/2025 - Completed | https://jira.jnj.com/browse/AFPM-3093
OTIF FIFO | Gxp | Ramesh | Abhishek Kumar | Yes | Type 1 | EM_SCM_OTIF-FIFO_R1.45 | Issue | 2/14/2025 - Unable to login to JDE Portal
Ethicon CO Reminders | Non-Gxp | Ramesh | Ayush | Updated | Type 1 | NA_QNC_Ethicon-CO-Reminders_R1.16_02122025 | YTS | ENV update pending
RSC-Flag Automation | Gxp | Ayush | Ayush | Re-work | Type 1 | EM_SCM_MD-QNC-RSC-FLAG_R1.7 | YTS | Scenario1 : Completed Scenario 2: waiting for test data
RSC-RAD Restrictions | Gxp | Ayush | Ayush | Yes | Type 1 | GL_SCM_RSC-RAD_R1.7 | Completed | 2/11/2025 - Completed | https://jira.jnj.com/browse/AGCJ-3897
JJV Agile & Qumas Export Print | Gxp | Ramesh | Balaji | Updated | Type 1 | GL_QNC_JJVBOT_R1.15 | Completed | 2/12/2025 - Completed | https://jira.jnj.com/browse/JDYX-107
LATAM Invoice Rejection | Non-Gxp | Ramesh | Balaji | Yes | Type 1 | LA_SCM_MT-Invoice-Rejection-Mgmt_R1.6_02042025 | Completed | 2/13/2025 - Completed | https://jira.jnj.com/browse/ADGF-7141
SA Quotation PhaseII | Non-Gxp | Bharath | Bharath | Yes | Type 2 | EM_SCM_SAQuotation_R2.24_02052025 | Issue | 2/10/2025- Outlook UI has upgraded due to that bot failed to send an email.
US Demand Split and Allocation | Gxp | Bharath | Bharath | Yes | Type 1 | NA_SCM_BWI-USDemand-Split_R1.6 | Issue | 2/10/2025- Popup is not populated once file is uploaded | https://jira.jnj.com/browse/AGCJ-3895
BRQC CARE(Contracted Automated Review Examiner) | Non-Gxp | Ashish | Chandana | Updated | Type 2 | NA_RnD_CARE_R1.35_02062025 | Completed | 2/6/2025 - Completed | https://jira.jnj.com/browse/AEZE-5717
VTMF Document Upload | Gxp | Ramesh | Chandana | Yes | Type 1 | NA_RnD_V-TMF_R1.18 | Completed | 2/4/2025 - Completed | https://jira.jnj.com/browse/AEZE-5706
Analysis Output Consistency Check | Non-Gxp | Sameera | Chandana | Updated | Type 1 | NA_RnD_OutputConsistency_R1.30_02052025 | Completed | 2/5/2025 - Completed | https://jira.jnj.com/browse/AEZE-5707
eLIMS User Access Review Automation | Gxp | Ramesh | Dilip | Updated | Type 2 | EM_SCM_UserAccessPR_R1.7 | Issue | 2/11/2025 - eLIMS Jaspersoft Launch Failure
RAVE Refresh Views | Non-Gxp | Sameera | Harsha | Yes | Type 1 | NA_RnD_RAVERefreshViews_R1.24_02032025 | Completed | 2/4/2025 - Completed | https://jira.jnj.com/browse/AEZE-5705
MASR EMEA | Gxp | Harsha | Harsha | Yes | Type 1 | EM_RnD_MASR_V2_R1.7 | Completed | 2/5/2025 - Completed | https://jira.jnj.com/browse/AEZE-5718 https://jira.jnj.com/browse/AEZE-5719
ZOE R3-Abiliti Overnight/Acuvue Ability | Non-Gxp | Bharath | Himabindu | Yes | Type 2 | GL_SCM_ABILITIRPABOT_R2.7_02042025 | Completed | 2/11/2025: Acuvue: Completed 2/10/2025-ZOE: Completed | Acuvue: https://jira.jnj.com/browse/ADGF-7140 ZOE: https://jira.jnj.com/browse/ADGF-7139
ETS PQMS Complaints Management | Gxp | Ramesh | Lokesh | Updated | Type 2 | EM_QnC_ETS-PQMS-ComplaintsManagement_R2.28 | In progress | Waiting for SE confirmation | https://jira.jnj.com/browse/AFSH-378
BWI AP Process Automation | Non-Gxp | Ramesh | Piyush | Yes | Type 1 | EM_SCM_MT-PL-BWI-INTERNALAP_R1.6_02042025 | Completed | 2/7/2025 - Completed | https://jira.jnj.com/browse/ADGF-7137
RSC - PARM Data Migration | Gxp | Piyush | Piyush | Updated | Type 1 | EM_SCM_RSCPARMDataMigration_R1.23 | Completed | 2/13/2025 - Completed | https://jira.jnj.com/browse/AFSR-21839
USROTC RAD Supply Preference | Gxp | Piyush | Piyush | Yes | Type 2 | EM_SCM_USROTC_RAD_SupplyPref_R1.19 | Completed | 2/7/2025 - Completed | https://jira.jnj.com/browse/AEZX-1984
G3O Invoicing | Non-Gxp | Ashish | Pravin | Updated | Type 1 | EM_RnD_G3OINVOICING-V2_R1.10_02062025 | Completed | 2/7/2025 - Completed | https://jira.jnj.com/browse/AEZE-5725
RAP Safety | Non-Gxp | Pravin | Pravin | Yes | Type 1 | NA_RnD_RAP_R1.55_02032025 | Completed | 2/7/2025 - Completed | https://jira.jnj.com/browse/AEZE-5724
Rebate Payments Phase 2 | Non-Gxp | Pravin | Pravin | Yes | Type 2 | NA_SCM_CSM-CA-REBATESPP_R2.36_02072025 | Issue | 2/14/202 - Tabulate Rebate Payment Report : Exception PDF Snapshot
DMR Automation | Non-Gxp | Priya | Priya | Updated | Type 2 | LA_SCM_MT-MYMEDI-DMR-AUTOCREATE-SFDC_R1.16_02062025 | Completed | 2/12/2025 - Completed
Missed Shipment Communication | Non-Gxp | Ashish | Priya | Yes | Type 2 | NA_SCM_CSS_MissShippComm_R1.24_02042025 | Completed | 2/6/2025 - Completed | https://jira.jnj.com/browse/ADGF-7130
Sales Order Creation | Gxp | Ashish | Priya | Yes | Type 2 | GL_SCM_SalesOrderCreation_R1.36 | In progress |  | https://jira.jnj.com/browse/AGCJ-3899
CMO Onboarding | Non-Gxp | Ashish | Rekha | Updated | Type 2 | EM_SCM_CMO_ONBOARDING_R1.8_02062025 | Hold - Redeployment | 2/7/2025 - Object missing
DCS Product Conversion | Gxp | Rekha | Rekha | Yes | Type 2 | NA_SCM_VC_WMS_ProductConversion_R1.3 | YTS | Waiting for test data from SE
IPIM MAILBOX RECONCILIATION_MainProcess | Non-Gxp | Yaswanth | Rekha | No release required | Type 1 | No release required | Issue | 2/14/2025 - Unable to find the file - '\\na.jnj.com\ncsusdfsroot\ERPA\IPDOCKETING\MAILBOXRECONCILIATION\IPDOCKETING_DEVCloudPC_RECON_ConfigFile.json '.
CSM Medicaid CLD | Non-Gxp | Ashish | Lokesh | Yes | Type 1 | NA_SCM_CSM_MedicaidCLD_R3.52_02042025 | YTS | 2/13/2025 - Requested test data from business
ClinMVReport | Non-Gxp | Sameera | Sameera | Yes | Type 1 | EM_RnD_CLINMV_Reports_ R1.16_02032025 | Completed | 2/4/2025 - Completed | https://jira.jnj.com/browse/AEZE-5703
Custom RAVE Reports | Non-Gxp | Sameera | Sameera | Yes | Type 1 | NA_RnD_Custom-Rave-Report_R1.59_02122025 | Issue | 2/14/2025 - File not found
Flex QOP | Non-Gxp | Ramesh | Sameera | Updated | Type 1 | GL_RnD_QOP_R1.9_02052025 | Completed | 2/6/2025 - Completed | https://jira.jnj.com/browse/AEZE-5726
Simple Submission Readiness Checks | Non-Gxp | Sandip | Sandip | Yes | Type 1 | NA_RND_SSRC_R1.24_01292025 | Completed | 2/4/2025 - Completed | https://jira.jnj.com/browse/AEZE-5704
WebTos | Gxp | Sandip | Sandip | Updated | Type 1 | GL_RnD_WebTOS_R1.21 | Issue | 2/11/2025 - Unable to identify RimDoc application window
CS Clinical Distribution | Gxp | Ashish | Sireesha | Yes | Type 2 | EM_SCM_CS-CLINICALDISTRIBUTION_R1.14 | Issue | 2/13/2025 - Failed to extract data from ACTIVE trials SSU 2.0.xlsx file using OLEDB Connection. | https://jira.jnj.com/browse/ADGF-7031

## QA Testing list
Automation Name | Compliance | Test data | Testing Completion Date | Release in 7.0 | Release in 7.3.1 | Code overwritten in 7.3.1 | Code change required | QA Testing Plan
US Demand Split and Allocation | GxP | Yes | 13/11/2024 | NA_SCM_BWI-USDemand-Split_R1.5_09172024 | NA_SCM_BWI-USDemand-Split_R1.4_06172024 | 2024-10-11 | No | Day 1
eCRF&aECG | GxP |  | 22/11/2024 | NA_RnD_ECRFAECG_R1.18_09272024 | NA_RnD_ECRFAECG_R1.16_07242024 | 15/11/2024 | Yes
DMR Automation | Non-GxP | Yes | 21/11/2024 | LA_SCM_MT-MYMEDI-DMR-AUTOCREATE-SFDC_R1.14_07082024 | LA_SCM_MT-MYMEDI-DMR-AUTOCREATE-SFDC_R1.14_07082024 | 22/10/2024 | No
Master File & Open Items | Non-GxP |  | 2024-02-12 | GL_FIN_MASTERFILEOPENITEMS_R2.1_11262024 | GL_FIN_MASTERFILEOPENITEMS_R1.8 | 15/11//2024 | Yes
Case Narrative | Non-GxP | Yes | 13/11/2024 | NA_RnD_CASENARRATIVES_R2.4_12102024 | NA_RnD_CASENARRATIVES_R2.2_12032024 | 2024-10-10 | Yes
MSR Reports | Non-GxP | Yes | 13/11/2024 | NA_IT_MSRREPORTS_R6.3_07182024 | NA_IT_MSRREPORTS_R6.3_07182024 | 2024-07-11 | No
ClinMVReport | Non-GxP | Yes | 2024-04-12 | EM_RnD_CLINMV_Reports_ R1.15_06132024 | EM_RnD_CLINMV_Reports_ R1.15_06132024 | 26/11/2024 | No
Custom RAVE Reports | Non-GxP | Yes | 2024-04-12 | NA_RnD_Custom-Rave-Report_R1.58_12202024 | NA_RnD_Custom-Rave-Report_R1.58_12202024 | 2024-12-12 | No
RAP Safety | Non-GxP | Yes | 2024-11-12 | NA_RnD_RAP_R1.54_12132024 | NA_RnD_RAP_R1.54_12132024 | 13/12/2024 | No
Summit - User Training Management | GXP |  | 15/11/2024 | GL_HR_CQ-SUMMIT-ALDA_R2.15_10152024 | GL_HR_CQ-SUMMIT-ALDA_R2.17_11262024 | 26/11/2024 | Yes | Day 2
MASR EMEA | GxP | Yes | 2024-04-12 | EM_RnD_MASR_V2_R1.6_10092024 | EM_RnD_MASR_V2_R1.6_10092024 | 2024-04-12 | No
Analysis Output Consistency Check | Non-GxP |  | 2025-03-01 | NA_RnD_OutputConsistency_R1.28_12012023 | NA_RnD_OutputConsistency_R1.28_12012023 | 18/12/2024 | No
CSM Medicaid CLD | Non-GxP |  | 2025-03-01 | NA_SCM_CSM_MedicaidCLD_R3.50_10172023 | NA_SCM_CSM_MedicaidCLD_R3.51_10252024 | 31/12/2024 | No
SCG eLOC Automation - Vizient | Non-GxP | Yes | 2024-10-12 | NA_HMD_SCG-VIZIENT_R1.25_07292024 | NA_HMD_SCG-VIZIENT_R1.25_07292024 | 2024-07-12 | No
IPIM MAILBOX RECONCILIATION_MainProcess | Non-GxP | Yes | 17/12/2024 | GL_LAW_IPIMMAILBOXRECONCILIATION_R1.5_08062024 | GL_LAW_IPIMMAILBOXRECONCILIATION_R1.5_08062024 | 31/7/2024 | No
JJRC Audit Automation | Non-GxP | Yes | 18/12/2024 | GL_SCM_JJRCAUDIT_R2.0_06142024 | GL_SCM_JJRCAUDIT_R2.0_06142024 | 13/12/2024 | No
SA Quotation PhaseII | Non-GxP | Yes | 30/12/2024 | EM_SCM_SAQuotation_R2.23_10012024 | EM_SCM_SAQuotation_R2.22_08292024 | 28/8/2024 | No
RAVE Refresh Views | Non-GxP | Yes | 31/12/2024 | NA_RnD_RAVERefreshViews_R1.23_12062024 | NA_RnD_RAVERefreshViews_R1.23_12062024 | 31/12/2024 | No
JJV Agile & Qumas Export Print | GxP |  | 2025-06-01 | GL_QNC_JJVBOT_R1.11_11132024 | GL_QNC_JJVBOT_R1.11_11132024 | 2025-06-01 | No | Day 3
DEPUY - CoA & CoS Certificates Automation | GxP | Yes | 17/12/2024 | GL_QNC_COACOSGENERATION_R1.16_11262024 | GL_QNC_COACOSGENERATION_R1.16_11262024 | 13/12/2024 | No
Ethicon CO Reminders | Non-GxP | Yes | 2024-09-12 | NA_QNC_Ethicon-CO-Reminders_R1.13_06232023 | NA_QNC_Ethicon-CO-Reminders_R1.14_07122024 | 19/11/2024 | No
CADTH web scraping | Non-GxP | Yes | 2024-05-12 | NA_SnM_CADTH-Web-Scraping_R1.37_11272024 | NA_SnM_CADTH-Web-Scraping_R1.36_11222024 | 22/11/2024 | Yes
BWI AP Process Automation | Non-GxP | Yes | 2024-04-12 | EM_SCM_MT-PL-BWI-INTERNALAP_R1.5_08192024 | EM_SCM_MT-PL-BWI-INTERNALAP_R1.5_08192024 | 2024-03-12 | No
Flex QOP | Non-GxP | Yes | 2024-11-12 | GL_RnD_QOP_R1.7_07082024 | GL_RnD_QOP_R1.7_07082024 | 2024-11-12 | No
SCG Contracting Management – eLOC HPG | Non-GxP | Yes | 2024-12-12 | NA_HMD_SCG-HPG_R1.25_11012024 | NA_HMD_SCG-HPG_R1.26_01132025 | 13/1/2025 | Yes
LATAM Invoice Rejection | Non-GxP | Yes | 2025-08-01 | LA_SCM_MT-Invoice-Rejection-Mgmt_R1.5_10072024 | LA_SCM_MT-Invoice-Rejection-Mgmt_R1.5_10072024 | 2025-08-01 | No
Rebate Payments Phase 2 | Non-GxP |  | 2025-10-01 | NA_SCM_CSM-CA-REBATESPP_R2.35_11212024 | NA_SCM_CSM-CA-REBATESPP_R2.35_11212024 | 2025-10-01 | No
RSC - PARM Data Migration | GxP | Yes | 27/12/2024 | EM_SCM_RSCPARMDataMigration_R1.21_03282024 | EM_SCM_RSCPARMDataMigration_R1.21_03282024 | 20/12/2024 | No | Day 4
VTMF Document Upload | GxP | Yes | 2024-05-12 | NA_RnD_V-TMF_R1.17_09122024 | NA_RnD_V-TMF_R1.16_10062023 | 29/11/2024 | No
Dispute Resolution P1 P2 | Non-GxP |  | 2025-07-01 | NA_SCM_CSS-DISPUTERESOLUTION_R1.20_05182023 NA_SCM_CSS-DISPUTERESOLUTION_V2_R1.22_12312024 | NA_SCM_CSS-DISPUTERESOLUTION_R1.20_05182023 NA_SCM_CSS-DISPUTERESOLUTION_V2_R1.21_11122024 | 2025-07-01 | No
BRQC CARE(Contracted Automated Review Examiner) | Non-GxP |  | 2025-09-01 | NA_RnD_CARE_R1.33_10232024 | NA_RnD_CARE_R1.33_10232024 | 13/12/2024 | No
ZOE R3-Abiliti Overnight | Non-GxP |  | 2025-01-10 | GL_SCM_ABILITIRPABOT_R2.6_10152024 GL_SCM_ABILITIRPABOT_V2_R1.10_10262022 GL_SCM_ABILITIRPABOT_V3_R1.7_01032024 | GL_SCM_ABILITIRPABOT_R2.6_10152024 GL_SCM_ABILITIRPABOT_V2_R1.10_10262022 GL_SCM_ABILITIRPABOT_V3_R1.7_01032024 | 15/10/2024 | No
Missed Shipment Communication | Non-GxP |  | 2025-07-01 | NA_SCM_CSS_MissShippComm_R1.23_05022024 | NA_SCM_CSS_MissShippComm_R1.23_05022024 | 2025-07-01 | No
CMO Onboarding | Non-GxP |  |  | EM_SCM_CMO_ONBOARDING_R1.7_06092023 | EM_SCM_CMO_ONBOARDING_R1.7_06092023
Document Reference Replacement | Non-GxP |  | 2025-07-01 | NA_QNC_DOC_REFERENCE_REPLACEMENT_R1.9_08302924 | NA_QNC_DOC_REFERENCE_REPLACEMENT_R1.9_08302924 | 2025-06-01 | No
Simple Submission Readiness Checks | Non-GxP |  | 2025-09-01 | NA_RND_SSRC_R1.23_12032024 | NA_RND_SSRC_R1.23_12032024 | 2025-08-01 | No
ETS PQMS Complaints Management | GxP |  | 13/1/2025 | EM_QnC_ETS-PQMS-ComplaintsManagement_R2.25_11072024 | M_QnC_ETS-PQMS-ComplaintsManagement_R2.25_11072024 | 2025-10-01 | No | Day 5
eLIMS User Access Review Automation | GxP |  | 15/1/2025 | EM_SCM_UserAccessPR_R1.5_10292024 | EM_SCM_UserAccessPR_R1.5_10292024 | 15/1/2025 | No
Sales Order Creation | GxP |  | 2025-08-01 | GL_SCM_SalesOrderCreation_R1.37_12092024 | GL_SCM_SalesOrderCreation_R1.35_10242024 | 2025-08-01 | No
RSC-RAD Restrictions | GxP |  | 13/1/2025 | GL_SCM_RSC-RAD_R1.6_05072024 | GL_SCM_RSC-RAD_R1.6_05072024 | 24/12/2024 | No
DCS Product Conversion | SOX |  | 14/1/2025 | NA_SCM_VC_WMS_ProductConversion_R1.2_12052024 | NA_SCM_VC_WMS_ProductConversion_R1.2_12052024 | 14/1/2025 | No
CS Clinical Distribution
WebTos
Joints & Mitek
G3O Invoicing
USROTC RAD Supply preference |  |  | 15/1/2025 | EM_SCM_USROTC_RAD_SupplyPref_R1.18_10242024 | EM_SCM_USROTC_RAD_SupplyPref_R1.18_10242024

## Impediments
Process Name | Developer | Impediments | Action Items | Issue Reported Dates | Issue Resolved Dates | Comments
Dispute Resolution P1 P2 | Ashish |  | PostgreSQL30 drives needs to be set up | 2024-03-12 | 2024-04-12 | Driver set up completed by platform Team
Dispute Resolution P1 P2 | Ashish |  | SAP application was locked | 2024-05-12 | 2024-05-12 | The user was locked and same is resolved with help of Application team
BRQC CARE(Contracted Automated Review Examiner) | Ashish |  | requested for VI Modeler access | 2024-05-12 | 2024-06-12 | VI Modeler access approved
EMEA Invoice Extract&Deliver | Ramesh |  | requested for VI Modeler access,Blueprism not installed, Test Data requested | 2024-04-12 | 2024-06-12 | Received test data, Vi-modeler request raised
SCG Contracting Management – eLOC HPG | Ramesh |  | requested for VI Modeler access,Blueprism not installed,Installation of Target App | 2024-04-12 | 2024-06-12 | Completed - Vi modeler access and BP installation, SE requested Prod Bot access
Flex QOP | Ramesh |  | Blueprism not installed, | 2024-05-12 | 2024-06-12 | Blueprism installed today once requested today after raising a request , facing some Macro issues and requested Prod bot access
ETS PQMS Complaints Management | Ramesh |  | requested for VI Modeler access,Blueprism not installed | 2024-04-12 |  | Completed
R&D JEISR | Yaswanth |  | Support Engineer is Fixing Bug in Dev | 26/11/2024 |  | Mbox application upgraded in lower environment / Dev In Progress- ON HOLD due to bug fixes, process improvement & enhancement
DEPUY - CoA & CoS Certificates Automation | Yaswanth |  | Oracle is not yet installed due to issue with appstore | 27/11/2024 | 2024-04-12 | Installation completed
R&D Submission Checks | Yaswanth |  | JaAdobe version is NA Appstore team | 22/11/2024 |  | Adobe is not available from jnj appstore
Latam Customer Order Intake | Yaswanth |  | Support Engineer has reached out to Business for new Test Data | 2024-10-12 |  | Given Test Data is not working to work on SAP
RAP Safety | Anil |  | GraphAPI_Mail-DEV-RND | 2024-05-12 | 2024-06-12 | Raise the request with platform team waiting for their confirmation (Got resloved)
SDIA / Trails 2 You | Anil |  | Config is completed, enhancement is going on | 2024-05-12 | 2024-05-12 | enhancement is going on, Kept Hold this process untill enhencement.
RND ESDCAQ | Anil |  | Waiting for test cases | 16/12/2024 |  | Raise the request with platform team to create the folder path in network , waiting for their confirmation , Witing for test cases from Business (Got Resolved), waiting for the happy path test case..
Rebate Payments Phase 2 | Anil |  | GraphAPI_Mail-DEV-RND and V-TMF_DEV_VI-1072 | 2024-09-12 | 2024-12-12 | Raise the request with platform team waiting for their confirmation (Got resloved), Waiting for test cases from Business. (Got resolved), debugging the process.
DCS Product Conversion | Anil |  | rundcs.cmd-QA | 17/12/2024 |  | SE is sent a email to business for get the rundcs.cmd application to download.
Analysis Output Consistency Check | Sameera |  | Java Installation is blocked by Appstore team | 19/12/2024 |  | Need to install java in cloud pc to resolve the python query execution issue.
Middle East K5 Trn | Yaswanth |  | ODBC is not supported | 2025-01-03 | 2025-01-07 | ODBC version is not supported in Bot

## Sheet2
Processs | Complexity | Primary | Secondary | Hostname | VI ID | Developer | Completion date | Configured
US Demand Split and Allocation |  | Bharath |  | RPA-VI222-QCSNY |  | Bharath | 13/11/2024 | Completed
DMR Automation |  | Priya |  | RPA-VI220-SO8J7 |  |  | 21/11/2024 | Completed
Master File & Open Items |  | Rishi |  | RPA-VI220-MRTYJ |  | Rishi | 2024-02-12 | Completed
LATAM Invoice Rejection |  | Balaji |  | RPA-VI220-2EHH8 |  | Ramesh | 2024-08-01 | Completed
CART MVP2 |  | Rishi |  | RPA-VI215-Y7HEI
eCRF&aECG |  | Suraj |  | RPA-VI211-JOREB |  | Ashish | 22/11/2024 | Completed
Summit - User Training Management |  | Bharath |  | RPA-VI213-J6XF2 |  | Bharath | 15/11/2024 | Completed
ADAM Submission Check |  | Haribabu |  | RPA-VI206-225FH |  | Haribabu |  | Completed
Case Narrative - R2 |  | Sandip |  | RPA-VI204-OWPEN |  |  | 13/11/2024
CAR-T |  | Rishi |  | RPA-VI107-R2C71 |  | Yaswanth |  | Completed
MSR Reports |  | Abhishek H |  | RPA-VI111-IINCU |  |  | 13/11/2024 | Completed
RND ESDCAQ | Complex | Pravin | Suraj | RPA-VI107-K6OA3 |  | Pravin |  | Completed
Rebate Payments Phase 2 | Medium | Pravin | Sameera | RPA-VI109-39THP |  | Pravin |  | Completed
RAP Safety | Simple | Pravin | Suraj | RPA-VI206-6CXFS |  | Pravin | 2024-12-11 | Completed
JJRC Audit Automation | Medium | Abhishek Kumar | Abhishek H | RPA-VI211-AI01M | VI-2114 | Yaswanth | 24/12/24 | Completed
DEPUY - CoA & CoS Certificates Automation | Medium | Abhishek Kumar | Prajnashree | RPA-VI214-FIL9B |  | Yaswanth | 17/12/2024 | Completed
IPIM MAILBOX RECONCILIATION_MainProcess | Simple | Rekha | Rishi | RPA-VI207-P0214 | VI-2072 | Yaswanth |  | Completed
EMEA Invoice Extract&Deliver | Medium | Dilip | Piyush | RPA-VI208-EIG7R |  | Ramesh |  | Completed
SCG Contracting Management – eLOC HPG | Complex | Priya | Piyush | RPA-VI213-6O4GT |  | Ramesh | 2024-12-12 | Completed
Missed Shipment Communication | Simple | Priya | Sireesha | RPA-VI209-GTF5H |  | Ashish | 2025-07-01 | Completed
Sales Order Creation | Medium | Priya | Himabindu | RPA-VI207-4DHFL |  | Ashish | 2025-08-01 | Completed
SMOX Invoice Recon | Medium | Balaji | Piyush | RPA-VI221-DK4XK
Flex QOP | Complex | Sameera | Pravin | RPA-VI213-RBTMA |  | Ramesh | 2024-12-11 | Completed
ClinMVReport | Simple | Sameera | Chandana | RPA-VI206-498FF |  | Sameera | 26/11/2024 | Completed
Custom RAVE Reports | Medium | Sameera | Suraj | RPA-VI206-498FF |  | Sameera | 2024-04-12 | Completed
VTMF Document Upload | Medium | Chandana | Harsha | RPA-VI115-8WL0N |  | Ramesh | 2024-05-12 | Completed
Analysis Output Consistency Check | Medium | Chandana | Haribabu | RPA-VI204-P0POJ |  | Sameera | 2025-03-01 | Completed
BRQC CARE(Contracted Automated Review Examiner) | Medium | Chandana | Pravin | RPA-VI118-W6CZF |  | Ashish | 2025-09-01 | Completed
R&D JEISR | Medium | Haribabu | Chandana | RPA-VI221-HCG9A |  | Yaswanth | 24/1/2025 | Completed
R&D Submission Checks | Medium | Haribabu | Sandip | RPA-VI101-03X5Z |  | Ashish |  | Completed
MASR EMEA | Medium | Harsha | Pravin | RPA-VI102-TBIM1 |  | Harsha | 2024-04-12 | Completed
SDIA / Trails 2 You | Medium | Harsha | Pravin | RPA-VI215-0DON3 |  | Harsha |  | Completed
DCS Product Conversion | Medium | Rekha | Lokesh | RPA-VI223-TGORG |  | Rekha | 14/1/2025 | Completed
RSC Flag Automation | Complex | Ayush | Bharath | RPA-VI221-RB8JK |  | Ayush | 20/1/2025 | Completed
Ethicon CO Reminders | Simple | Ayush | Chandana | RPA-VI120-33DHA |  | Ramesh | 29/11/2024 | Completed
ETH Manual Order Allocation | Medium | Ayush | Sameera | RPA-VI114-96Z97 |  | Yaswanth |  | Completed
ZOE R3-Abiliti Overnight | Medium | Himabindu | Abhishek H | RPA-VI211-UUNIT |  | Bharath |  | Completed
Dispute Resolution P1 P2 | Simple | Himabindu | Sireesha | RPA-VI206-EVPR4 |  | Ashish | 2025-07-01 | Completed
Acuvue Ability | Medium | Himabindu | Abhishek Kumar | RPA-VI200-00I97 |  | Bharath | 16/1/2025 | Completed
HR TM - Summit Learning Request Intake | Simple | Himabindu | Abhishek M | RPA-VI114-5ZHPN |  |  | Decomissioned
ETS PQMS Complaints Management | Complex | Lokesh | Tahreem | RPA-VI208-OWMBY | VI-2085 | Ramesh | 13/1/2025 | Completed
CSM Medicaid CLD | Medium | Lokesh | Bharath | RPA-VI200-UV5B7 | VI-2005 | Ashish | 2025-03-01 | Completed
SCG eLOC Automation - Vizient | Complex | Piyush | Priya | RPA-VI212-P6VLI |  | Piyush | 2024-10-12 | Completed
USROTC RAD Supply Preference | Medium | Piyush | Abhishek Kumar | RPA-VI207-UAWHE |  | Piyush | 15/1/2025 | Completed
LATAM Customer Order Intake | Medium | Piyush | Himabindu | RPA-VI205-37N6H |  | Yaswanth/Piyush |  | Completed
BWI AP Process Automation | Simple | Piyush | Priya | RPA-VI218-GD1B4 |  | Ramesh | 2024-04-12 | Completed
CS Clinical Distribution | Medium | Sireesha | Ayush | RPA-VI221-TD20E |  | Ashish | 21/1/2025 | Completed
R&D EISFAF | Medium | Suraj | Haribabu | RPA-VI115-GAHFL |  | Ramesh |  | Completed
JJV Agile & Qumas Export Print | Medium | Balaji | Tahreem | RPA-VI214-LK3W6 |  | Ramesh |  | Completed
Simple Submission Readiness Checks | Complex | Sandip | Haribabu | RPA-VI208-5LWVR |  | Sandip | 2025-09-01 | Completed
Printing of Finished Good Labels from PRISYM 360 | Medium | Abhishek H | Himabindu | RPA-VI215-HG8R1 |  | Abhishek H |  | Completed
Small Molecule Digital Release | Complex | Lokesh | Ayush | RPA-VI214-26K1G |  | Ramesh |  | Completed
CADTH web scraping | Simple | Abdul | Lokesh | RPA-VI116-86OYX |  | Ramesh | 26/11/2024 | Completed
Order Entry Automation – Fusion | Medium | Abdul | Abhishek H | RPA-VI213-21D53 |  | Ramesh |  | Completed
Brazil Warehouse | Medium | RISHI | Priya | RPA-VI219-9QL03 |  | Rishi |  | Completed
RSC-RAD Restrictions |  | Ayush |  | RPA-VI221-RB8JK |  | Ayush | 13/1/2025 | Completed
Tax - Indiebot |  | Abhishek H | Abhishek Kumar | RPA-VI104-0SZW5 |  | Abhishek H
Inventory Reconciliation GMED |  | Abhishek H | Lokesh | RPA-VI204-ER21U | VI-2047
Document Reference Replacement |  | Abhishek Kumar | Balaji | RPA-VI200-E6M4W |  | Yaswanth | 2025-07-01
Controlled Substance Data Collection |  | Abhishek Kumar | Sugavardhan | RPA-VI214-5JLX0 | VI-2147 | Yaswanth
OTIF FIFO |  | Abhishek Kumar | Priya | RPA-VI109-VL62E | VI-1094 | Ramesh | 17/1/2025
Backorder Allocation |  | Ayush | Dilip | RPA-VI105-9WTB2 |  | Ramesh
SA Quotation PhaseII |  | Bharath | Sireesha | RPA-VI208-SLSLP |  | Bharath | 30/12/2024
RAD Supply Preference |  | Bharath | Himabindu | RPA-VI204-ZBK9E | VI-2045 | Bharath
eLIMS User Access Review Automation |  | Dilip | Abhishek Kumar | RPA-VI215-MQ9NH |  | Ramesh | 15/1/2025
IP DOCKETING |  | Rekha | Rishi | RPA-VI217-2KFDM |  | Ramesh
LA_SCM_MT-SAP-CONTRACTCREATION |  | Dilip | Himabindu | RPA-VI219-IEGE0 |  | Ashish
Middle East K5 Creation |  | Dilip | Abdul | RPA-VI204-NUZTU | VI-2042 | Yaswanth
Participant & Site Journey Maps |  | Haribabu | Pravin | RPA-VI209-ML3P9 | VI-2095 | Yaswanth
Product Load into MDRIM |  | Harsha | Bharath | RPA-VI218-MEDAP | Vi-2182 | Yaswanth
RAVE Refresh Views |  | Harsha | Chandana | RPA-VI110-CG7UD | VI-1106 | Sameera | 31/12/2024
Non GMED PO |  | Himabindu | Sireesha | RPA-VI204-T8WMN |  | Himabindu
Finish Goods Optimization |  | Himabindu | Dilip | RPA-VI203-4Q1KC |  | Ashish
HCP Payments Germany |  | Piyush | Rishi | RPA-VI221-I8O21 |  | Ashish
RSC - PARM Data Migration |  | Piyush | Priya | RPA-VI203-SXGXE |  | Ashish | 27/12/2024
GR MATCH |  | Piyush | Bharath | RPA-VI110-CW7EF |  | Piyush
G3O Invoicing |  | Pravin | Harsha | RPA-VI205-4V9LO |  | Ashish
Spine TECA Manual allocation |  | Rekha | Balaji | RPA-VI214-LL18X |  | Ashish
CMO Onboarding |  | Rekha | Dilip | RPA-VI214-5JLX0 | VI-2147 | Ashish
Joints & Mitek |  | Rekha | Abhishek H | RPA-VI218-FEHXT |  | Ashish
WebTos |  | Sandip | Harsha | RPA-VI215-IFLUJ |  | Anil | 16/1/2025
RPA-GL-PHM-RND-CMS (NeuroScience) |  | Sandip | V | RPA-VI217-VJ1RV |  | Anil
Croom PO Generation |  | Sireesha | Sameera | RPA-VI207-0B0X5 |  | Sameera
Raw Material Release |  | Sireesha | Dilip | RPA-VI217-JXP7E |  | Anil
QA Master Data |  | Sugavardhan | Lokesh | RPA-VI220-ONXMC |  | Ashish
Atlas Material Flag for deletion |  | Sugavardhan | Suraj | RPA-VI220-ONXMC |  | Ramesh
Archiving Auto Index |  | Suraj | Sandip | RPA-VI213-XNSBO |  | Anil
SPACE User Access |  | Haribabu | Sameera | RPA-VI209-MO0V0 | VI-2092 | Yaswanth
CRO Site Payments v2 |  | Haribabu | Sandip |  |  | Ramesh
Tender Header Analysis-Detection | [7 empty] | Abbyy process
Turkey Order Automation |  | Priya | Lokesh |  |  | Ramesh
PBG Zoller
ASPAC Vision I2C | [7 empty] | Abbyy process
SC Plan PO Management EMEA |  | Rekha | Ayush | RPA-VI104-54N4P | VI-1043 | Ramesh
HR TA - ORW Offer Generation | [5 empty] | Ashish
Change Admin (CA) Check II |  | Abdul | Rekha |  |  | Ashish
OMP Omega |  | Shreyank
DPS SAFETY STOCK |  | Shreyank |  |  |  | Ashish
PO Confirmation Update in SAP System
WorkOrder Due Date Automation |  | Balaji | Dilip |  |  | Ashish
Returns Management - RGA Sharing |  | Shreyank | Pravin |  |  | Ashish
Order Monitoring Automation |  | Rishi | Bharath |  |  | Ashish
ME Order Automation |  | Sireesha | Bharath |  |  | Ashish
ICP-SAP BTB LATAM COMMERCIAL Yearend (H) |  | Shreyank |  |  |  | Ashish
CSM Chargeback |  | Balaji | Abdul
CSM Pay Package |  | Sireesha | Ayush |  |  | Anil
GCC Reporting |  | Suraj | Piyush |  |  | Yaswanth
SCG eLOC Premier |  | Priya | Piyush
Task Reminders & Escalations |  | Abhishek Kumar | Balaji |  |  | Ramesh
CSM Medicaid Invoice Phase-1 and 2 |  | Sireesha | Ayush |  |  | Ramesh
CORE Chargebacks |  | Balaji | Abdul |  |  | Yaswanth
BWI Manual Allocation |  | Sugavardhan | Priya |  |  | Ramesh
RA-VARIATIONS-OUTCOMES_MainProcess |  | Bharath | Rekha |  |  | Anil
NA_RND_RAVE_UPDATE_USERACCESS |  | Haribabu | Sandip |  |  | Sameera
GCO Site Manager Training - RED Chatbot |  | Chandana

## Automations in production
Processs | Sent for pc provisioning -12/18/2024
Acuvue Ability | SPACE User Access
ADAM Submission Check | CRO Site Payments v2
Analysis Output Consistency Check | Turkey Order Automation
Archiving Auto Index | SC Plan PO Management EMEA
ASPAC Vision I2C | Change Admin (CA) Check II
Atlas Material Flag for deletion | OMP Omega
Backorder Allocation | DPS SAFETY STOCK
Brazil Warehouse | WorkOrder Due Date Automation
BRQC CARE(Contracted Automated Review Examiner) | Returns Management - RGA Sharing
BWI AP Process Automation | Order Monitoring Automation
BWI Manual Allocation | ME Order Automation
CADTH web scraping | CSM Chargeback
CAR-T | CSM Pay Package
Case Narrative | Janssen Select
Change Admin (CA) Check II | GCC Reporting
ClinMVReport | SCG eLOC Premier
CMO Onboarding | Task Reminders & Escalations
Controlled Substance Data Collection | CSM Medicaid Invoice Phase-1 and 2
CORE Chargebacks | CORE Chargebacks
CRO Site Payments v2 | BWI Manual Allocation
Croom PO Generation | GCO Site Manager Training - RED Chatbot
CS Clinical Distribution | RA-VARIATIONS-OUTCOMES_MainProcess
CSM Chargeback | NA_RND_RAVE_UPDATE_USERACCESS
CSM Medicaid CLD
CSM Medicaid Invoice Phase-1 and 2
CSM Pay Package
Custom RAVE Reports
DCS Product Conversion
DEPUY - CoA & CoS Certificates Automation
Dispute Resolution P1 P2
DMR Automation
Document Reference Replacement
DPS SAFETY STOCK
eCRF&aECG
eLIMS User Access Review Automation
EMEA Invoice Extract&Deliver
ETH Manual Order Allocation
Ethicon CO Reminders
ETS PQMS Complaints Management
Finish Goods Optimization
Flex QOP
G3O Invoicing
GCC Reporting
GCO Site Manager Training - RED Chatbot
GR MATCH
HCP Payments Germany
HR TM - Summit Learning Request Intake
ICP-SAP BTB LATAM COMMERCIAL Yearend (H)
Inventory Reconciliation GMED
IP DOCKETING
IPIM MAILBOX RECONCILIATION_MainProcess
Janssen Select
JJRC Audit Automation
JJV Agile & Qumas Export Print
Joints & Mitek
LA_SCM_MT-SAP-CONTRACTCREATION
LATAM Customer Order Intake
LATAM Invoice Rejection
MASR EMEA
Master File & Open Items
ME Order Automation
Middle East K5 Creation
Missed Shipment Communication
MSR Reports (Decommison- Out of Scope)
NA_RND_RAVE_UPDATE_USERACCESS
Non GMED PO
OMP Omega
Order Entry Automation – Fusion
Order Monitoring Automation
OTIF FIFO
Participant & Site Journey Maps
PIPE-Line Import
Printing of Finished Good Labels from PRISYM 360
Product Load into MDRIM
QA Master Data
R&D EISFAF
R&D JEISR
R&D Submission Checks
RAD Supply Preference
RAP Safety
RA-VARIATIONS-OUTCOMES_MainProcess
RAVE Refresh Views
Rebate Payments Phase 2
Returns Management - RGA Sharing
RND ESDCAQ
RPA-GL-PHM-RND-CMS (NeuroScience)
RSC - PARM Data Migration
RSC Flag Automation
RSC-RAD Restrictions
SA Quotation PhaseII
Sales Order Creation
SC Plan PO Management EMEA
SCG Contracting Management – eLOC HPG
SCG eLOC Automation - Vizient
SCG eLOC Premier
SDIA / Trails 2 You
Simple Submission Readiness Checks
Small Molecule Digital Release
SMOX Invoice Recon
SPACE User Access
Summit - User Training Management
Task Reminders & Escalations
Tax - Indiebot
Tender Header Analysis-Detection
Turkey Order Automation
US Demand Split and Allocation
USROTC RAD Supply Preference
VTMF Document Upload
WebTos
WorkOrder Due Date Automation
ZOE R3-Abiliti Overnight
Tender Header Analysis-Detection
ASPAC Vision I2C